Kim Kickoff Meeting

30 minutes — Garen + Ana + Kim — Week of Feb 17

Meeting Purpose

Get Kim oriented and aligned on her first project. She should leave this call knowing exactly what to do, who to ask, and what "done" looks like.

Agenda

Time

Topic

0:00–5:00

Intros and context

How Kim got connected to OEFF. What excites her about this. Quick round of who does what.

5:00–15:00

OEFF in plain language (Ana leads)

•	
      What the festival is: community venues screening environmental films across Chicagoland

•	
      What this year looks like: ~15+ venues, April 22–28, distributed model with contractors

•	
      Where communication breaks down: multiple channels, unclear routing, everything funneling through 2–3 people

•	
      What we're hoping Kim can help with: fresh perspective on whether our docs and processes make sense to someone who doesn't already know everything

15:00–22:00

The starter project (Garen walks through)

•	
      What she's reviewing: host guide, team docs site, host communication templates

•	
      The three anchor questions: What's unclear? What's missing? What could be systematized?

•	
      Where the materials live: Google Drive folder + NotebookLM workspace

•	
      Timeline: ~6–8 hours over 10 days, deliverable is an audit summary in whatever format feels natural

•	
      Compensation: $40/hr, drawn from collaborator pool

22:00–27:00

Logistics

•	
      Primary contact: Garen for day-to-day questions

•	
      Check-in: quick sync after ~1 week

•	
      Communication: email or text, whatever Kim prefers

•	
      Confirm access: Google Drive shared, NotebookLM set up

27:00–30:00

Questions and close

Open floor. Anything unclear? Anything she wants to know about the team or the org before diving in?

Before the Meeting (Garen's Prep)

•	
      Create Google Drive folder "OEFF — Kim Onboarding" with curated 12-doc reading list

•	
      Set up NotebookLM notebook with the same docs

•	
      Send Kim the proposal (.docx) and starter project brief before the call

•	
      Confirm calendar invite with Ana and Kim

After the Meeting

•	
      Kim starts independent review

•	
      Garen checks in at ~1 week mark

•	
      Kim delivers audit summary at ~10 days

•	
      30-min debrief call: Garen + Kim (Ana optional)

•	
      Decide together whether to move to Phase 2

What success looks like: Kim understands the org well enough to spot structural issues, not just surface ones. We get honest signal about whether her process background translates. Low onboarding cost — the review is the onboarding.