# OEFF 2026 — Starter Project

Host venue communications onboarding

Scope: 8–10 hours over 2 weeks
Working style: Kickoff call + async, then figure out a good meeting cadence
Rate: At the moment, we're able to offer $40/hr

## The project

OEFF's host venue communications — webinar reminders, screening materials, check-ins — need to run on a reliable schedule as the festival approaches (April–May). We've recently built some new infrastructure: shared inboxes, templates, a communications plan. The role here is to step in and operate it, as well as document along the way.

We have host info sessions over the next few months and have just set up a mail merge campaign — looking to schedule regular reminders and continue to flesh out our process here.

Where we are: OEFF is in year one of moving from manual coordination to platform-based infrastructure — shared inboxes, a centralized host guide, webinar registration through Zoom. The tools are working, but the team is still building muscle memory. There's a communications plan, dependency maps, and email templates already built — the work is to operate it, improve it, and write down what the next person would need to know.

## What you'd work with

Operational tools (day one access):

Host Communications Plan — 5 communication streams with templates, schedule, and tool stack (YAMM, Google Sheets, Gmail)

Dependency Map — prerequisites, approval chains, and rollback plans for every send

hosts@ shared inbox — the Gmail account host communications send from

Host Guide (hosts.oneearthfilmfest.org) — the persistent reference hosts are pointed to in every email

Background context (provided at kickoff):

Venue tier system — how OEFF classifies and supports different venue types

Team roster — who does what, who approves what

Contractor agreement — scope, budget, and team structure

## How it works

Kickoff (30 min sync) — Walk through the comms plan, the dependency map, and the hosts@ inbox. I'll demo one send cycle end-to-end and answer initial questions.

Shadow week (~3 hours) — Read the comms plan and dependency map, watch a live webinar reminder cycle (YAMM merge, sheet update, host guide update), ask questions async. By the end of the week you should be ready to send.

Send week (~5–7 hours) — Take over Stream 1 (webinar reminders and recording follow-ups) with me as backup. Follow the templates and the dependency map, and keep a running doc of friction points and gaps.

Deliverable: Operator notes + improved templates — A running doc of what you needed to know that wasn't written down, plus any template or process improvements you made along the way. Honest notes from doing the work, not a formal report.

Debrief (30 min sync) — Walk through what worked, what didn't, and what to hand off next.

## Three things to track as you work

What tripped you up? Where did the process assume context you didn't have? What required a question that should have been answered by the docs?

What's missing from the handoff? If someone else needed to do this next year, what would you write down for them that doesn't exist yet?

What could be tighter? Where do you see repeated patterns that could become templates, checklists, or standard sequences?

## Broader work I'm interested in exploring

This starter project is a bite-sized way to work together and see how the fit feels. Beyond host comms, there are a few areas where I think collaboration could be valuable:

Internal documentation and systems adoption — we've been building a lot of new tools and processes (shared inboxes, Airtable, a centralized host guide), and how we roll them out to the team matters as much as the tools themselves

Operator guides — turning the running notes from this project into a repeatable playbook, so the next person doesn't start from scratch

Expanding to more communication streams — deliverables shipping, data collection forms, and host check-ins as the festival approaches

Festival week venue coordination — on-the-ground host support during April 22–28

Post-festival retrospective — a structured debrief while everything is still fresh

None of these are committed — they're possibilities that give shape to what a longer collaboration could look like. This is a project-based engagement, not a formal role. We're still figuring out what roles the org actually needs.